## Read me
Welcome to Project Status Dashboard Toolkit
Using this toolkit, you can make a dynamic, self-updating dashboard for your projects in no time.
Who can use this dashboard?
You need to have basic excel knowledge to start using this dashboard. It is designed keeping you in mind.
How to make changes to the dashboard?
To make changes to the dashboard, you need to change values in the worksheets - Data, Gantt Chart, Burndown Chart and Issue Trakcer.
Once you make the changes in these worksheets, just revisit the "project status dashboard" worksheet to see it updated.
How can I make changes to the dashboard charts?
You can insert your own charts in to this dashboard very easily. First, insert a new worksheet and make a chart there with all the data and formatting. Once the chart is ready, just cut and paste it in the dashboard. Adjust the chart's size and position and you are good to go.

## Project Status Dashboard
Project Status |  | Completed |  | 23% |  | Outstanding Issues
Ongoing Activities |  |  | Project Plan |  | Click on the gantt chart to see it in detail
Activity | % done
Top 5 Issues
Find test manager
Descope Risky Items
Start System Testing
Find more money
Demo to user group
Burndown Chart |  |  |  |  | Project Timeline
Report prepared by XYZ | [6 empty] | 2021-08-31
Project Status Dashboard
Project Name

## Data
Enter Project Status |  | Enter the Project Milestone Data Here |  |  |  | Top 5 Issues
Overall Project Status | Green | ID | Date | Milestone if any | Height | Issue
Overall Project Progress | 23% | 1 | 2012-03-17 | Project Kickoff | 2 | Find test manager
|  | 2 | 2012-04-16 | First Prototype | 3 | Descope Risky Items
|  | 3 | 2012-05-07 | Investor Presentation | 1 | Start System Testing
|  | 4 | 2012-05-31 | Alpha Out | 2 | Find more money
|  | 5 | 2012-07-10 | Private Beta Out | 3 | Demo to user group
|  | 6 | 2012-08-31 | Public Beta | 1
|  | 7 | 2012-10-20 | Roll out | 2
|  | 8 | 2012-12-09 | Plan for future | 3
|  | 9 |  |  | 3
|  | 10 |  |  | 3
|  | 11 |  |  | 3
|  | 12 |  |  | 3
|  | 13 |  |  | 3
|  | 14 |  |  | 3
|  | 15 |  |  | 3
|  | 16 |  |  | 3
|  | 17 |  |  | 3
|  | 18 |  |  | 3
|  | 19 |  |  | 3
|  | 20 |  |  | 3
|  | 21 |  |  | 3
|  | 22 |  |  | 3
|  | 23 |  |  | 3
|  | 24 |  |  | 3
|  | 25 |  |  | 3
|  | 26 |  |  | 3
|  | 27 |  |  | 3
|  | 28 |  |  | 3
|  | 29 |  |  | 3
|  | 30 |  |  | 3
|  | 31 |  |  | 3
|  | 32 |  |  | 3
|  | 33 |  |  | 3
|  | 34 |  |  | 3
|  | 35 |  |  | 3
|  | 36 |  |  | 3
|  | 37 |  |  | 3
|  | 38 |  |  | 3
|  | 39 |  |  | 3
|  | 40 |  |  | 3
Formulas:
Date = MIN(tblPlan[Plan Start])
Date = [Date, row above]+RANDBETWEEN(20,60)
Enter dates & Milestones here

## Gantt Chart
[13 empty] | 40980 | 40981 | 40982 | 40983 | 40984 | 40987 | 40988 | 40989 | 40990 | 40991 | 40994 | 40995 | 40996 | 40997 | 40998 | 41001 | 41002 | 41003 | 41004 | 41005 | 41008 | 41009 | 41010 | 41011 | 41012 | 41015 | 41016 | 41017 | 41018 | 41019 | 41022 | 41023 | 41024 | 41025 | 41026 | 41029 | 41030 | 41031 | 41032 | 41033 | 41036 | 41037 | 41038 | 41039 | 41040 | 41043 | 41044 | 41045 | 41046 | 41047 | 41050 | 41051 | 41052 | 41053 | 41054 | 41057 | 41058 | 41059 | 41060 | 41061 | 41064 | 41065 | 41066 | 41067 | 41068 | 41071 | 41072 | 41073 | 41074 | 41075
[13 empty] | 40980: 2012-03-12; 40987: 2012-03-19; 40994: 2012-03-26; 41001: 2012-04-02; 41008: 2012-04-09; 41015: 2012-04-16; 41022: 2012-04-23; 41029: 2012-04-30; 41036: 2012-05-07; 41043: 2012-05-14; 41050: 2012-05-21; 41057: 2012-05-28; 41064: 2012-06-04; 41071: 2012-06-11 | Plan |  | Actual |  | Overlap
ID | Activity | Plan Start | Plan Duration | Actual Start | Actual Duration | % Done | ID |  | Activity | Plan Start | % Done |  | 40980: 2012-03-12; 40987: 2012-03-19; 40994: 2012-03-26; 41001: 2012-04-02; 41008: 2012-04-09; 41015: 2012-04-16; 41022: 2012-04-23; 41029: 2012-04-30; 41036: 2012-05-07; 41043: 2012-05-14; 41050: 2012-05-21; 41057: 2012-05-28; 41064: 2012-06-04; 41071: 2012-06-11 | Start | End | Start | End | Start | End
1 | Activity 1 | 2012-03-17 | 13 | 2012-03-16 | 13 | 44% | 1 |  | Activity 1 | 2012-03-17 | 44% | 0.44 | [70 empty] | 2012-03-17 | 2012-04-04 | 2012-03-16 | 2012-04-04 | 2012-03-17 | 2012-04-04
2 | Activity 2 | 2012-03-27 | 11 | 2012-04-01 | 13 | 98% | 2 |  | Activity 2 | 2012-03-27 | 98% | 0.98 | [70 empty] | 2012-03-27 | 2012-04-11 | 2012-04-01 | 2012-04-18 | 2012-04-01 | 2012-04-11
3 | Activity 3 | 2012-03-30 | 12 | 2012-04-02 | 14 | 82% | 3 |  | Activity 3 | 2012-03-30 | 82% | 0.82 | [70 empty] | 2012-03-30 | 2012-04-17 | 2012-04-02 | 2012-04-20 | 2012-04-02 | 2012-04-17
4 | Activity 4 | 2012-04-11 | 7 | 2012-04-12 | 6 | 71% | 4 |  | Activity 4 | 2012-04-11 | 71% | 0.71 | [70 empty] | 2012-04-11 | 2012-04-20 | 2012-04-12 | 2012-04-20 | 2012-04-12 | 2012-04-20
5 | Activity 5 | 2012-04-14 | 11 | 2012-04-11 | 13 | 31% | 5 |  | Activity 5 | 2012-04-14 | 31% | 0.31 | [70 empty] | 2012-04-14 | 2012-04-30 | 2012-04-11 | 2012-04-30 | 2012-04-14 | 2012-04-30
6 | Activity 6 | 2012-04-28 | 8 | 2012-05-08 | 11 | 33% | 6 |  | Activity 6 | 2012-04-28 | 33% | 0.33 | [70 empty] | 2012-04-28 | 2012-05-09 | 2012-05-08 | 2012-05-23 | 2012-05-08 | 2012-05-09
7 | Activity 7 | 2012-05-03 | 5 | 2012-05-09 | 4 | 100% | 7 | 1 | Activity 7 | 2012-05-03 | 100% | 1 | [70 empty] | 2012-05-03 | 2012-05-10 | 2012-05-09 | 2012-05-15 | 2012-05-09 | 2012-05-10
8 | Activity 8 | 2012-05-11 | 13 | 2012-05-18 | 17 | 66% | 8 |  | Activity 8 | 2012-05-11 | 66% | 0.66 | [70 empty] | 2012-05-11 | 2012-05-30 | 2012-05-18 | 2012-06-12 | 2012-05-18 | 2012-05-30
9 | Activity 9 | 2012-05-25 | 6 | 2012-06-04 | 9 | 97% | 9 |  | Activity 9 | 2012-05-25 | 97% | 0.97 | [70 empty] | 2012-05-25 | 2012-06-04 | 2012-06-04 | 2012-06-15 | 2012-06-04 | 2012-06-04
10 | Activity 10 | 2012-06-05 | 6 | 2012-06-09 | 4 | 80% | 10 |  | Activity 10 | 2012-06-05 | 80% | 0.8 | [70 empty] | 2012-06-05 | 2012-06-13 | 2012-06-09 | 2012-06-14 | 2012-06-09 | 2012-06-13
11 | Activity 11 | 2012-06-09 | 7 | 2012-06-09 | 6 | 70% | 11 |  | Activity 11 | 2012-06-09 | 70% | 0.7 | [70 empty] | 2012-06-09 | 2012-06-19 | 2012-06-09 | 2012-06-18 | 2012-06-09 | 2012-06-18
12 | Activity 12 | 2012-06-12 | 8 | 2012-06-29 | 10 | 99% | 12 |  | Activity 12 | 2012-06-12 | 99% | 0.99 | [70 empty] | 2012-06-12 | 2012-06-22 | 2012-06-29 | 2012-07-13 | 2012-03-11 | 2012-03-11
13 | Activity 13 | 2012-06-15 | 13 | 2012-06-19 | 17 | 100% | 13 | 1 | Activity 13 | 2012-06-15 | 100% | 1 | [70 empty] | 2012-06-15 | 2012-07-04 | 2012-06-19 | 2012-07-12 | 2012-06-19 | 2012-07-04
14 | Activity 14 | 2012-06-28 | 9 | 2012-07-03 | 8 | 92% | 14 |  | Activity 14 | 2012-06-28 | 92% | 0.92 | [70 empty] | 2012-06-28 | 2012-07-11 | 2012-07-03 | 2012-07-13 | 2012-07-03 | 2012-07-11
15 | Activity 15 | 2012-07-03 | 7 | 2012-07-11 | 6 | 43% | 15 |  | Activity 15 | 2012-07-03 | 43% | 0.43 | [70 empty] | 2012-07-03 | 2012-07-12 | 2012-07-11 | 2012-07-19 | 2012-07-11 | 2012-07-12
16 | Activity 16 | 2012-07-06 | 5 | 2012-07-07 | 8 | 80% | 16 |  | Activity 16 | 2012-07-06 | 80% | 0.8 | [70 empty] | 2012-07-06 | 2012-07-13 | 2012-07-07 | 2012-07-18 | 2012-07-07 | 2012-07-13
17 | Activity 17 | 2012-07-13 | 4 | 2012-07-19 | 6 | 94% | 17 |  | Activity 17 | 2012-07-13 | 94% | 0.94 | [70 empty] | 2012-07-13 | 2012-07-19 | 2012-07-19 | 2012-07-27 | 2012-07-19 | 2012-07-19
18 | Activity 18 | 2012-07-17 | 12 | 2012-07-23 | 13 | 39% | 18 |  | Activity 18 | 2012-07-17 | 39% | 0.39 | [70 empty] | 2012-07-17 | 2012-08-02 | 2012-07-23 | 2012-08-09 | 2012-07-23 | 2012-08-02
19 | Activity 19 | 2012-07-23 | 6 | 2012-07-31 | 4 | 24% | 19 |  | Activity 19 | 2012-07-23 | 24% | 0.24 | [70 empty] | 2012-07-23 | 2012-07-31 | 2012-07-31 | 2012-08-06 | 2012-07-31 | 2012-07-31
20 | Activity 20 | 2012-07-27 | 5 | 2012-08-02 | 7 | 62% | 20 |  | Activity 20 | 2012-07-27 | 62% | 0.62 | [70 empty] | 2012-07-27 | 2012-08-03 | 2012-08-02 | 2012-08-13 | 2012-08-02 | 2012-08-03
21 | Activity 21 | 2012-08-04 | 11 | 2012-08-05 | 10 | 79% | 21 |  | Activity 21 | 2012-08-04 | 79% | 0.79 | [70 empty] | 2012-08-04 | 2012-08-20 | 2012-08-05 | 2012-08-17 | 2012-08-05 | 2012-08-17
22 | Activity 22 | 2012-08-09 | 7 | 2012-08-14 | 8 | 94% | 22 |  | Activity 22 | 2012-08-09 | 94% | 0.94 | [70 empty] | 2012-08-09 | 2012-08-20 | 2012-08-14 | 2012-08-24 | 2012-08-14 | 2012-08-20
23 | Activity 23 | 2012-08-20 | 10 | 2012-08-27 | 13 | 88% | 23 |  | Activity 23 | 2012-08-20 | 88% | 0.88 | [70 empty] | 2012-08-20 | 2012-09-03 | 2012-08-27 | 2012-09-13 | 2012-08-27 | 2012-09-03
24 | Activity 24 | 2012-08-29 | 11 | 2012-09-04 | 12 | 77% | 24 |  | Activity 24 | 2012-08-29 | 77% | 0.77 | [70 empty] | 2012-08-29 | 2012-09-13 | 2012-09-04 | 2012-09-20 | 2012-09-04 | 2012-09-13
25 | Activity 25 | 2012-09-09 | 6 | 2012-09-09 | 8 | 56% | 25 |  | Activity 25 | 2012-09-09 | 56% | 0.56 | [70 empty] | 2012-09-09 | 2012-09-17 | 2012-09-09 | 2012-09-19 | 2012-09-09 | 2012-09-17
26 | Activity 26 | 2012-09-20 | 7 | 2012-09-18 | 11 | 27% | 26 |  | Activity 26 | 2012-09-20 | 27% | 0.27 | [70 empty] | 2012-09-20 | 2012-10-01 | 2012-09-18 | 2012-10-03 | 2012-09-20 | 2012-10-01
27 | Activity 27 | 2012-09-30 | 8 | 2012-10-04 | 10 | 46% | 27 |  | Activity 27 | 2012-09-30 | 46% | 0.46 | [70 empty] | 2012-09-30 | 2012-10-10 | 2012-10-04 | 2012-10-18 | 2012-10-04 | 2012-10-10
28 | Activity 28 | 2012-10-12 | 10 | 2012-10-22 | 8 | 92% | 28 |  | Activity 28 | 2012-10-12 | 92% | 0.92 | [70 empty] | 2012-10-12 | 2012-10-26 | 2012-10-22 | 2012-11-01 | 2012-10-22 | 2012-10-26
29 | Activity 29 | 2012-10-23 | 10 | 2012-10-21 | 12 | 91% | 29 |  | Activity 29 | 2012-10-23 | 91% | 0.91 | [70 empty] | 2012-10-23 | 2012-11-06 | 2012-10-21 | 2012-11-06 | 2012-10-23 | 2012-11-06
30 | Activity 30 | 2012-10-27 | 5 | 2012-10-31 | 8 | 90% | 30 |  | Activity 30 | 2012-10-27 | 90% | 0.9 | [70 empty] | 2012-10-27 | 2012-11-02 | 2012-10-31 | 2012-11-12 | 2012-10-31 | 2012-11-02
31 | Activity 31 | 2012-11-05 | 6 | 2012-11-06 | 5 | 39%
32 | Activity 32 | 2012-11-09 | 6 | 2012-11-15 | 4 | 34%
33 | Activity 33 | 2012-11-09 | 4 | 2012-11-09 | 6 | 87%
34 | Activity 34 | 2012-11-09 | 5 | 2012-11-09 | 9 | 57%
35 | Activity 35 | 2012-11-09 | 10 | 2012-11-09 | 13 | 27%
36 | Activity 36 | 2012-11-24 | 9 | 2012-11-25 | 8 | 93%
37 | Activity 37 | 2012-11-30 | 12 | 2012-12-04 | 16 | 40%
38 | Activity 38 | 2012-12-12 | 6 | 2012-12-09 | 8 | 50%
39 | Activity 39 | 2012-12-16 | 6 | 2012-12-23 | 9 | 66%
40 | Activity 40 | 2012-12-21 | 5 | 2012-12-28 | 8 | 39%
41 | Activity 41 | 2012-12-30 | 7 | 2013-01-06 | 11 | 50%
42 | Activity 42 | 2013-01-03 | 4 | 2013-01-07 | 2 | 67%
43 | Activity 43 | 2013-01-06 | 10 | 2013-01-07 | 14 | 75%
44 | Activity 44 | 2013-01-13 | 5 | 2013-01-10 | 7 | 63%
45 | Activity 45 | 2013-01-16 | 9 | 2013-01-17 | 12 | 64%
46 | Activity 46 | 2013-01-23 | 14 | 2013-01-20 | 18 | 66%
47 | Activity 47 | 2013-01-29 | 10 | 2013-01-28 | 12 | 86%
48 | Activity 48 | 2013-02-08 | 6 | 2013-02-18 | 10 | 36%
49 | Activity 49 | 2013-02-14 | 6 | 2013-02-19 | 10 | 96%
50 | Activity 50 | 2013-02-19 | 10 | 2013-02-23 | 10 | 63%
51 | Activity 51 | 2013-03-01 | 8 | 2013-03-08 | 6 | 59%
52 | Activity 52 | 2013-03-13 | 14 | 2013-03-12 | 14 | 99%
53 | Activity 53 | 2013-03-22 | 4 | 2013-03-23 | 3 | 70%
54 | Activity 54 | 2013-03-25 | 9 | 2013-03-30 | 9 | 48%
55 | Activity 55 | 2013-03-27 | 7 | 2013-03-28 | 7 | 75%
56 | Activity 56 | 2013-04-05 | 5 | 2013-04-05 | 5 | 59%
57 | Activity 57 | 2013-04-17 | 10 | 2013-04-18 | 9 | 78%
58 | Activity 58 | 2013-04-19 | 14 | 2013-04-21 | 15 | 51%
59 | Activity 59 | 2013-04-25 | 14 | 2013-05-03 | 12 | 58%
60 | Activity 60 | 2013-05-01 | 14 | 2013-05-08 | 13 | 77%
61 | Activity 61 | 2013-05-04 | 9 | 2013-05-03 | 7 | 71%
62 | Activity 62 | 2013-05-12 | 4 | 2013-05-19 | 7 | 33%
63 | Activity 63 | 2013-05-14 | 6 | 2013-05-24 | 9 | 26%
64 | Activity 64 | 2013-05-24 | 13 | 2013-05-30 | 13 | 56%
65 | Activity 65 | 2013-05-29 | 4 | 2013-05-31 | 2 | 59%
66 | Activity 66 | 2013-06-05 | 13 | 2013-06-07 | 13 | 25%
67 | Activity 67 | 2013-06-08 | 11 | 2013-06-15 | 9 | 67%
68 | Activity 68 | 2013-06-22 | 4 | 2013-06-20 | 5 | 80%
69 | Activity 69 | 2013-06-29 | 14 | 2013-06-30 | 18 | 100%
70 | Activity 70 | 2013-07-09 | 11 | 2013-07-06 | 9 | 31%
71 | Activity 71 | 2013-07-22 | 4 | 2013-07-30 | 2 | 91%
72 | Activity 72 | 2013-07-29 | 7 | 2013-08-07 | 10 | 88%
73 | Activity 73 | 2013-08-01 | 5 | 2013-08-04 | 4 | 75%
74 | Activity 74 | 2013-08-09 | 4 | 2013-08-16 | 6 | 32%
75 | Activity 75 | 2013-08-23 | 8 | 2013-08-26 | 10 | 68%
76 | Activity 76 | 2013-08-27 | 12 | 2013-09-02 | 12 | 77%
77 | Activity 77 | 2013-08-31 | 11 | 2013-09-07 | 11 | 60%
78 | Activity 78 | 2013-09-12 | 7 | 2013-09-09 | 7 | 78%
79 | Activity 79 | 2013-09-22 | 8 | 2013-09-25 | 9 | 71%
80 | Activity 80 | 2013-09-28 | 8 | 2013-10-06 | 10 | 49%
81 | Activity 81 | 2013-10-11 | 8 | 2013-10-11 | 10 | 73%
82 | Activity 82 | 2013-10-24 | 9 | 2013-11-01 | 8 | 68%
83 | Activity 83 | 2013-11-04 | 4 | 2013-11-14 | 3 | 85%
84 | Activity 84 | 2013-11-08 | 13 | 2013-11-18 | 15 | 99%
85 | Activity 85 | 2013-11-12 | 14 | 2013-11-16 | 13 | 33%
86 | Activity 86 | 2013-11-16 | 11 | 2013-11-24 | 9 | 31%
87 | Activity 87 | 2013-11-18 | 8 | 2013-11-17 | 7 | 77%
88 | Activity 88 | 2013-11-26 | 12 | 2013-11-28 | 15 | 94%
89 | Activity 89 | 2013-12-08 | 8 | 2013-12-10 | 11 | 63%
90 | Activity 90 | 2013-12-18 | 7 | 2013-12-25 | 8 | 96%
91 | Activity 91 | 2013-12-27 | 11 | 2014-01-03 | 10 | 77%
92 | Activity 92 | 2014-01-04 | 4 | 2014-01-12 | 3 | 59%
93 | Activity 93 | 2014-01-14 | 5 | 2014-01-11 | 4 | 100%
94 | Activity 94 | 2014-01-17 | 7 | 2014-01-17 | 7 | 44%
95 | Activity 95 | 2014-01-23 | 9 | 2014-02-01 | 8 | 67%
96 | Activity 96 | 2014-01-27 | 7 | 2014-02-02 | 5 | 98%
97 | Activity 97 | 2014-02-08 | 10 | 2014-02-08 | 12 | 60%
98 | Activity 98 | 2014-02-16 | 6 | 2014-02-18 | 7 | 27%
99 | Activity 99 | 2014-02-25 | 5 | 2014-02-28 | 8 | 42%
100 | Activity 100 | 2014-03-10 | 8 | 2014-03-07 | 10 | 97%
Note on E4: Duration in working days (excluding weekends and holidays)
Note on G4: Duration in working days (excluding weekends and holidays)
Show Gantt for:
Gantt Chart
Project Plan Data

## Burndown Chart
Burn down chart | [11 empty] | Don't edit this table
Deliverable Burn Down | [5 empty] | Budget Burn Down | [5 empty] | Selected Chart |  | 1
| Burned down |  | Balance |  | Daily Completed |  | Burned down |  | Balance |  | Daily Completed |  | Burned down |  | Balance |  | Daily Completed
Day | Planned | Actual | Planned | Actual |  | Day | Planned | Actual | Planned | Actual |  | Day | Planned | Actual | Planned | Actual
0 |  |  | 250 | 250 | #N/A | 0 |  |  | 436 | 436 | #N/A | 0 | 0 | 0 | 436 | 436 | #N/A
1 | 12 | 8 | 238 | 242 | 8 | 1 | 7 | 8 | 429 | 428 | 8 | 1 | 7 | 8 | 429 | 428 | 8
2 | 18 | 10 | 220 | 232 | 10 | 2 | 30 | 13 | 399 | 415 | 13 | 2 | 30 | 13 | 399 | 415 | 13
3 | 11 | 0 | 209 | 232 | 0 | 3 | 25 | 7 | 374 | 408 | 7 | 3 | 25 | 7 | 374 | 408 | 7
4 | 4 | 12 | 205 | 220 | 12 | 4 | 19 | 16 | 355 | 392 | 16 | 4 | 19 | 16 | 355 | 392 | 16
5 | 5 | 19 | 200 | 201 | 19 | 5 | 39 | 34 | 316 | 358 | 34 | 5 | 39 | 34 | 316 | 358 | 34
6 | 6 | 13 | 194 | 188 | 13 | 6 | 18 |  | 298 | #N/A | #N/A | 6 | 18 | 0 | 298 | #N/A | #N/A
7 | 10 | 8 | 184 | 180 | 8 | 7 | 37 | 14 | 261 | 344 | 14 | 7 | 37 | 14 | 261 | 344 | 14
8 | 20 | 2 | 164 | 178 | 2 | 8 | 22 | 27 | 239 | 317 | 27 | 8 | 22 | 27 | 239 | 317 | 27
9 | 20 |  | 144 | #N/A | #N/A | 9 | 5 | 17 | 234 | 300 | 17 | 9 | 5 | 17 | 234 | 300 | 17
10 | 18 | 2 | 126 | 176 | 2 | 10 | 16 | 19 | 218 | 281 | 19 | 10 | 16 | 19 | 218 | 281 | 19
11 | 6 |  | 120 | #N/A | #N/A | 11 | 24 | 8 | 194 | 273 | 8 | 11 | 24 | 8 | 194 | 273 | 8
12 | 13 | 2 | 107 | 174 | 2 | 12 | 2 | 41 | 192 | 232 | 41 | 12 | 2 | 41 | 192 | 232 | 41
13 | 7 | 34 | 100 | 140 | 34 | 13 | 32 | 27 | 160 | 205 | 27 | 13 | 32 | 27 | 160 | 205 | 27
14 | 14 |  | 86 | #N/A | #N/A | 14 | 26 |  | 134 | #N/A | #N/A | 14 | 26 | 0 | 134 | #N/A | #N/A
15 | 12 |  | 74 | #N/A | #N/A | 15 | 15 |  | 119 | #N/A | #N/A | 15 | 15 | 0 | 119 | #N/A | #N/A
16 | 14 |  | 60 | #N/A | #N/A | 16 | 20 |  | 99 | #N/A | #N/A | 16 | 20 | 0 | 99 | #N/A | #N/A
17 | 12 |  | 48 | #N/A | #N/A | 17 | 14 |  | 85 | #N/A | #N/A | 17 | 14 | 0 | 85 | #N/A | #N/A
18 | 11 |  | 37 | #N/A | #N/A | 18 | 39 |  | 46 | #N/A | #N/A | 18 | 39 | 0 | 46 | #N/A | #N/A
19 | 19 |  | 18 | #N/A | #N/A | 19 | 34 |  | 12 | #N/A | #N/A | 19 | 34 | 0 | 12 | #N/A | #N/A
20 | 18 |  | 0 | #N/A | #N/A | 20 | 12 |  | 0 | #N/A | #N/A | 20 | 12 | 0 | 0 | #N/A | #N/A
Enter data in these cells

## Issue Tracker
Issue Tracker Template
Date
# | Issue | Priority | Open | Close | Comments
1 | User name check fails | Low | 2012-02-01
2 | Password field is not mandatory | Medium | 2012-06-18
3 | Reset button doesn’t work | High | 2012-03-15 | 2012-03-24
4 | When window is maximized, the layout is compromised | Low | 2012-03-17 | 2012-03-27
5 | Password field takes more than 99 chars | Medium | 2012-01-23
6 | User name allows SQL injection | Medium | 2012-06-30 | 2012-07-14
7 | Password allows SQL injection | Low | 2012-05-08 | 2012-05-17
8 | User name allows HTML Injection | High | 2012-05-05
9 | Password allows HTML Injection | Low | 2012-05-04
10 | Submit doesn’t work on enter | Medium | 2012-02-01 | 2012-02-18
11 | User name is not the default field on screen load | High | 2012-07-12
12 | When hitting F5, the error message still remains | Low | 2012-02-12 | 2012-02-27
13 | Message is wrong | Medium | 2012-05-24
14 | User name check fails | Medium | 2012-06-20 | 2012-06-23
15 | Password field is not mandatory | Low | 2012-01-22
16 | Reset button doesn’t work | High | 2012-08-20
17 | When window is maximized, the layout is compromised | Medium | 2012-03-24 | 2012-04-13
18 | Password field takes more than 99 chars | High | 2012-09-06
19 | User name allows SQL injection | Low | 2012-04-14
20 | Password allows SQL injection | Medium | 2012-05-14 | 2012-05-17
21 | User name allows HTML Injection | Medium | 2012-05-14 | 2012-05-24
22 | Password allows HTML Injection | Low | 2012-07-05
23 | Submit doesn’t work on enter | High | 2012-04-15
24 | User name is not the default field on screen load | Low | 2012-09-09
25 | When hitting F5, the error message still remains | Medium | 2012-09-06
26 | Message is wrong | High | 2012-03-01
27 | User name check fails | Low | 2012-03-27
28 | Password field is not mandatory | Medium | 2012-08-03
29 | Reset button doesn’t work | Medium | 2012-04-02
30 | When window is maximized, the layout is compromised | Medium | 2012-06-21 | 2012-07-05
31 | Password field takes more than 99 chars | High | 2012-04-11
32 | User name allows SQL injection | Low | 2012-07-12 | 2012-07-17
33 | Password allows SQL injection | Medium | 2012-02-25 | 2012-03-02
34 | User name allows HTML Injection | Medium | 2012-04-05 | 2012-04-20
35 | Password allows HTML Injection | Low | 2012-08-27
36 | Submit doesn’t work on enter | High | 2012-08-01
37 | User name is not the default field on screen load | Low | 2012-03-14 | 2012-03-17
38 | When hitting F5, the error message still remains | Medium | 2012-02-19
39 | Message is wrong | High | 2012-04-07 | 2012-04-19
40 | User name check fails | Low | 2012-01-30 | 2012-02-07
41 | Password field is not mandatory | Medium | 2012-04-22 | 2012-05-08
42 | Reset button doesn’t work | Medium | 2012-04-03 | 2012-04-20
43 | When window is maximized, the layout is compromised | High | 2012-04-04
44 | Password field takes more than 99 chars | Low | 2012-03-12 | 2012-03-19
45 | User name allows SQL injection | Medium | 2012-08-30 | 2012-09-06
46 | Password allows SQL injection | High | 2012-05-27 | 2012-06-16
47 | User name allows HTML Injection | Low | 2012-04-22 | 2012-05-12
48 | Password allows HTML Injection | Medium | 2012-09-15 | 2012-10-03
49 | Submit doesn’t work on enter | Medium | 2012-07-25
50 | User name is not the default field on screen load | Medium | 2012-07-26 | 2012-07-30
51 | When hitting F5, the error message still remains | High | 2012-08-17
52 | Message is wrong | Low | 2012-05-27
53 | User name check fails | Medium | 2012-02-17
54 | Password field is not mandatory | Medium | 2012-08-14
55 | Reset button doesn’t work | Low | 2012-02-21 | 2012-02-27
56 | When window is maximized, the layout is compromised | High | 2012-09-01
57 | Password field takes more than 99 chars | Low | 2012-04-12 | 2012-04-28
58 | User name allows SQL injection | Medium | 2012-02-16
59 | Password allows SQL injection | High | 2012-07-22
60 | User name allows HTML Injection | Low | 2012-01-25

## Calculations
All the dashboard calculations are here
No. of ongoing Activities This week | 0 | The list of ongoing activities is automatically populated based on Project Plan. Overwrite values in the grayed portion to see your own list.
# | List of ongoing activities |  | List of ongoing Activities (cleaned) | Completion % | Total |  | Open Issue Summary |  |  | BurnDown Chart Types
1 | 0 | 1 |  |  | 100% |  | High | 12 |  | Budget
2 | 0 | 2 |  |  | 100% |  | Medium | 11 |  | Deliverables
3 | 0 | 3 |  |  | 100% |  | Low | 10
4 | 0 | 4 |  |  | 100%
5 | 0 | 5 |  |  | 100%
Today Details | Y
#N/A | 4
Calculations for Gantt Chart Do not modify this sheet
Gantt Start | 2012-03-16 |  | Plan | 1 |  | Show Plan | TRUE |  | Show Help? | FALSE
Weekday | 6 |  | Actual | 2 |  | Show Actual | FALSE |  | Gantt chart prepared on 15,Nov 2012. Showing activities 1 to 30 in dates 12 Mar '12 to 15 Jun '12
Start Monday | 2012-03-12 |  | Both | 3 |  | show Both | FALSE
Offset | 0
Offset Start | 2012-03-12 |  |  |  |  | 40979
Activity Offset | 0 |  | Display Option | 1 |  | Plan Start
[11 empty] | Chosen | Overlap
# | ID | Activity | Plan Start | Plan Duration | Actual Start | Actual Duration | % Done | Plan End | Actual End |  | Start | Start | End
1 | 1 | Activity 1 | 2012-03-17 | 13 | 2012-03-16 | 13 | 44% | 2012-04-04 | 2012-04-04 |  | 2012-03-17 | 2012-03-17 | 2012-04-04
2 | 2 | Activity 2 | 2012-03-27 | 11 | 2012-04-01 | 13 | 98% | 2012-04-11 | 2012-04-18 |  | 2012-03-27 | 2012-04-01 | 2012-04-11
3 | 3 | Activity 3 | 2012-03-30 | 12 | 2012-04-02 | 14 | 82% | 2012-04-17 | 2012-04-20 |  | 2012-03-30 | 2012-04-02 | 2012-04-17
4 | 4 | Activity 4 | 2012-04-11 | 7 | 2012-04-12 | 6 | 71% | 2012-04-20 | 2012-04-20 |  | 2012-04-11 | 2012-04-12 | 2012-04-20
5 | 5 | Activity 5 | 2012-04-14 | 11 | 2012-04-11 | 13 | 31% | 2012-04-30 | 2012-04-30 |  | 2012-04-14 | 2012-04-14 | 2012-04-30
6 | 6 | Activity 6 | 2012-04-28 | 8 | 2012-05-08 | 11 | 33% | 2012-05-09 | 2012-05-23 |  | 2012-04-28 | 2012-05-08 | 2012-05-09
7 | 7 | Activity 7 | 2012-05-03 | 5 | 2012-05-09 | 4 | 100% | 2012-05-10 | 2012-05-15 |  | 2012-05-03 | 2012-05-09 | 2012-05-10
8 | 8 | Activity 8 | 2012-05-11 | 13 | 2012-05-18 | 17 | 66% | 2012-05-30 | 2012-06-12 |  | 2012-05-11 | 2012-05-18 | 2012-05-30
9 | 9 | Activity 9 | 2012-05-25 | 6 | 2012-06-04 | 9 | 97% | 2012-06-04 | 2012-06-15 |  | 2012-05-25 | 2012-06-04 | 2012-06-04
10 | 10 | Activity 10 | 2012-06-05 | 6 | 2012-06-09 | 4 | 80% | 2012-06-13 | 2012-06-14 |  | 2012-06-05 | 2012-06-09 | 2012-06-13
11 | 11 | Activity 11 | 2012-06-09 | 7 | 2012-06-09 | 6 | 70% | 2012-06-19 | 2012-06-18 |  | 2012-06-09 | 2012-06-09 | 2012-06-18
12 | 12 | Activity 12 | 2012-06-12 | 8 | 2012-06-29 | 10 | 99% | 2012-06-22 | 2012-07-13 |  | 2012-06-12 | 2012-03-11 | 2012-03-11
13 | 13 | Activity 13 | 2012-06-15 | 13 | 2012-06-19 | 17 | 100% | 2012-07-04 | 2012-07-12 |  | 2012-06-15 | 2012-06-19 | 2012-07-04
14 | 14 | Activity 14 | 2012-06-28 | 9 | 2012-07-03 | 8 | 92% | 2012-07-11 | 2012-07-13 |  | 2012-06-28 | 2012-07-03 | 2012-07-11
15 | 15 | Activity 15 | 2012-07-03 | 7 | 2012-07-11 | 6 | 43% | 2012-07-12 | 2012-07-19 |  | 2012-07-03 | 2012-07-11 | 2012-07-12
16 | 16 | Activity 16 | 2012-07-06 | 5 | 2012-07-07 | 8 | 80% | 2012-07-13 | 2012-07-18 |  | 2012-07-06 | 2012-07-07 | 2012-07-13
17 | 17 | Activity 17 | 2012-07-13 | 4 | 2012-07-19 | 6 | 94% | 2012-07-19 | 2012-07-27 |  | 2012-07-13 | 2012-07-19 | 2012-07-19
18 | 18 | Activity 18 | 2012-07-17 | 12 | 2012-07-23 | 13 | 39% | 2012-08-02 | 2012-08-09 |  | 2012-07-17 | 2012-07-23 | 2012-08-02
19 | 19 | Activity 19 | 2012-07-23 | 6 | 2012-07-31 | 4 | 24% | 2012-07-31 | 2012-08-06 |  | 2012-07-23 | 2012-07-31 | 2012-07-31
20 | 20 | Activity 20 | 2012-07-27 | 5 | 2012-08-02 | 7 | 62% | 2012-08-03 | 2012-08-13 |  | 2012-07-27 | 2012-08-02 | 2012-08-03
21 | 21 | Activity 21 | 2012-08-04 | 11 | 2012-08-05 | 10 | 79% | 2012-08-20 | 2012-08-17 |  | 2012-08-04 | 2012-08-05 | 2012-08-17
22 | 22 | Activity 22 | 2012-08-09 | 7 | 2012-08-14 | 8 | 94% | 2012-08-20 | 2012-08-24 |  | 2012-08-09 | 2012-08-14 | 2012-08-20
23 | 23 | Activity 23 | 2012-08-20 | 10 | 2012-08-27 | 13 | 88% | 2012-09-03 | 2012-09-13 |  | 2012-08-20 | 2012-08-27 | 2012-09-03
24 | 24 | Activity 24 | 2012-08-29 | 11 | 2012-09-04 | 12 | 77% | 2012-09-13 | 2012-09-20 |  | 2012-08-29 | 2012-09-04 | 2012-09-13
25 | 25 | Activity 25 | 2012-09-09 | 6 | 2012-09-09 | 8 | 56% | 2012-09-17 | 2012-09-19 |  | 2012-09-09 | 2012-09-09 | 2012-09-17
26 | 26 | Activity 26 | 2012-09-20 | 7 | 2012-09-18 | 11 | 27% | 2012-10-01 | 2012-10-03 |  | 2012-09-20 | 2012-09-20 | 2012-10-01
27 | 27 | Activity 27 | 2012-09-30 | 8 | 2012-10-04 | 10 | 46% | 2012-10-10 | 2012-10-18 |  | 2012-09-30 | 2012-10-04 | 2012-10-10
28 | 28 | Activity 28 | 2012-10-12 | 10 | 2012-10-22 | 8 | 92% | 2012-10-26 | 2012-11-01 |  | 2012-10-12 | 2012-10-22 | 2012-10-26
29 | 29 | Activity 29 | 2012-10-23 | 10 | 2012-10-21 | 12 | 91% | 2012-11-06 | 2012-11-06 |  | 2012-10-23 | 2012-10-23 | 2012-11-06
30 | 30 | Activity 30 | 2012-10-27 | 5 | 2012-10-31 | 8 | 90% | 2012-11-02 | 2012-11-12 |  | 2012-10-27 | 2012-10-31 | 2012-11-02
Formulas:
List of ongoing activities = MIN(tblPlan[Plan Start],tblPlan[Actual Start])
List of ongoing activities = C54+[List of ongoing activities, row above]*7
List of ongoing Activities (cleaned) = INDEX(tblPlan[Plan Start],[List of ongoing activities])
Total = INDEX(tblPlan[Actual Start],[List of ongoing activities])
Plan End = WORKDAY([List of ongoing Activities (cleaned)],[Completion %])
Actual End = WORKDAY([Total],[Actual Duration])
Start = CHOOSE(F57,[List of ongoing Activities (cleaned)],[Total],[Total])
Start = IF(OR([Plan End]<[Total],[Actual End]<[List of ongoing Activities (cleaned)]),dummyDate,MAX([List of ongoing Activities (cleaned)],[Total]))
End = IF(OR([Plan End]<[Total],[Actual End]<[List of ongoing Activities (cleaned)]),dummyDate,MIN([Plan End]:[Actual End]))
Note on E5: Change this to see new activities in dashboard